## Timetable
Fresher's Week 2009
|  | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wednesday | 2009-09-30 |  |  |  |  | 1. COMMITTEE MEETING
Thursday | 2009-10-01
Friday | 2009-10-02 |  |  |  | 2. RE-FRESHERS
Saturday | 2009-10-03 |  | 6. PRAYER MEETING | 3. MOVING PEOPLE INTO HALLS
Sunday | 2009-10-04 |  | 4. HELPING RUN/FLYERING AT INTERNATIONAL RECEPTION
Monday | 2009-10-05 | 6. PRAYER MEETING |  |  |  | 5. PUTTING POSTERS UP FOR JAZZ NIGHT & INTERNATIONAL EVENT
Tuesday | 2009-10-06 | 6. PRAYER MEETING |  | 7. FRESHERS STALL/GAZEBO OR PRAYER ROOM
Wednesday | 2009-10-07
Thursday | 2009-10-08 | 9. PRAYER & FLYER FOR JAZZ NIGHT | [9 empty] | 10. SET UP & FLYER FOR JAZZ NIGHT | 11. LIVE JAZZ AND PIZZA NIGHT
Friday | 2009-10-09 | 8. PRAYER & FLYER FOR LUNCH BAR |  |  |  | 12. PICNIC AND CRAZY FUN ON QUEEN'S LAWN | [5 empty] | 13. INTERNATIONAL EVENT E.G. TOURS OF INTERNATIONAL CAFE'S IN LONDON
Saturday | 2009-10-10 | [9 empty] | 14. HALL SOCIALS
Sunday | 2009-10-11 |  | 15. MORNING CHURCH TOURS | [7 empty] | 16. EVENING CHURCH TOURS
Not yet agreed/no one responsible yet
Someone is responsible/in process of being organised
Finalised and completely organised

## Responsibilities
Number | Person(s) responsible | Main tasks involved
1 | Nathan
2 | Toby, Nathan, Seb, Emma Banks | Toby to put together some prayer points. Nath/Seb to communicate CU Vision for the year and Freshers week, fun activity (e.g. Bigger or better), dish out CU T-Shirts.
3 | Sam Scully | contact hall wardens for permission, organise teams to help at each hall
4 | Josh Uitterdijk | get permission from international office to volunteer with stewarding at international reception. Flyers and flyering for global cafe.
5 | Dave Akroyd | Publicity team to do this
6 | Toby Rowland | organising prayer points, room booking for prayer room, etc
7 | Emma Banks, Toby Rowland | Emma to organise posters, cupcakes, generally girly stuff, look into getting new banner. Two sign-up lists: Christians wanting to get stuck in, people just-looking. Box for Felix questionnaires. FREE Gospels, flyers for events later in the week, Fresher's Pack must be at stall. Toby to organise prayer points for prayer room.
8 | Toby Rowland | organising prayer points, room booking for prayer room, etc
9 | Toby Rowland | organising prayer points, room booking for prayer room, etc
10 | Zim Okoli | Zim to get a team to help with set up
11 | Zim Okoli | Musicians, Room booking, Decor, table cloths, lights, Food, drinks, plates & cups, FREE Gospels, other literature, flyers/notices for events later in week. Two sign-up sheets. Incorporate UCCF Lunchbox video on suffering.
12 | Zim Okoli | Zim to get someone off comm to organise this
13 | Josh Uitterdijl, Reuben? Edward Ip? | Josh to make sure publicity includes independent poster and flyer. E.g. For tour different teams to visit All Souls or TBT international cafe.
14 | Sam Scully/Relevant cell leaders | Sam to organise the cell leaders to run hall socials. Meet in halls, food, etc.
15 | John Raftery | need to decide which Churches we'll take Freshers to. Don't forget internationals (he can liase with Nath and Seb about that). Need a small team to take groups off to different churches.
16 | John Raftery
17 | Zim Okoli | two sign-up sheets
General publicity | Dave Akroyd | Dave to recruit a publicity team to delegate tasks or designing to. Managing production of all flyers, posters, organise a publicity team, consider doing some publicity in Mandarin and French etc.
A "Basic Freshers pack" - including details on Hub, Impact, Global Cafe, Website + maps/useful stuff, information about South Kensington.
Cell group advertising for each cell + any events they do in Freshers week (details from each cell leader)
Any one off-events we are doing in Freshers week (e.g. lunchtime talk) (details from each person in charge)
CU T-Shirts. T-Shirts are just simple ICCU logo + website.